## Sheet1
ID | Finding | Risk Level | Business Impact | Recommendation
R1 | File integrity monitoring is not implemented on production servers. | High | Malicious changes may go undetected. | Implement File Integrity Monitoring (FIM) on all production servers.
R2 | ISO 27001 certification is not held by the vendor. | High | Reduced independent assurance of security controls. | Work towards ISO 27001 certification or provide equivalent assurance.
R3 | Server hardening excludes desktop systems. | Medium | Endpoints may be more vulnerable to attack. | Apply hardening standards to all managed desktops.
R4 | External security assessment evidence was not fully provided. | Medium | Limited visibility of the vendor's security posture. | Provide full security assessment or detailed evidence.
R5 | Incident response procedures have not been formally tested. | Medium | Incident response effectiveness cannot be verified. | Conduct and document regular incident response exercises.
R6 | Information protection policy is still under development. | Medium | Sensitive information may not be consistently protected. | Finalise and approve the information protection policy.
R7 | Checks and balances process remains under development. | Medium | Increased risk of inappropriate privileged access. | Complete and implement the access governance process.
R8 | Job transfer procedures are incomplete. | Medium | Excessive user access may remain after role changes. | Implement formal role transfer procedures.
R9 | Enterprise patch management requires further maturity. | Medium | Systems may remain vulnerable to known exploits. | Strengthen patch management governance and reporting.
R10 | Test environments do not have production-equivalent security controls. | Medium | Development environments may become attack vectors. | Apply equivalent security controls to test environments.
R11 | Critical vulnerabilities are remediated outside the required timeframe. | Medium | Delayed remediation increases exposure to cyber threats. | Reduce remediation time to meet organisational requirements.
R12 | High vulnerabilities exceed the recommended remediation timeframe. | Medium | Increased likelihood of exploitation. | Establish and monitor remediation SLAs.
R13 | Monthly access reviews are performed quarterly. | Medium | Excessive user permissions may remain undetected. | Review privileged access monthly.
R14 | Web server logs are reviewed monthly instead of weekly. | Medium | Delayed detection of malicious activity. | Increase web log review frequency.
R15 | Backup integrity testing occurs every six months instead of quarterly. | Medium | Backup failures may remain undetected. | Perform backup integrity testing quarterly.
R16 | Backups rely on password protection rather than encryption. | Medium | Backup data may be exposed if compromised. | Encrypt all backup media using industry-standard encryption.